## Sheet1
Repositories | S.No | Activity | Implemention Start Date | Implementation End Date | Status
dm-qa-spa & dm-qa-sap | 1 | Investigating Repository in Teamforge | 2021-10-19 | 2021-10-19 | Completed
| 2 | Configuration analysis in Jenkins | 2021-10-19 | 2021-10-19 | Completed
| 3 | Workflow Creation in GitHub Actions (For Manual & Automated Run) | 2021-10-20 | 2021-10-20 | Completed
| 4 | Testing The Workflow | 2021-10-20 |  | In Progress
| 5 | Document Preparation |  |  | Yet to Start

## Sheet2
Errors Identified While Testing The Workflow | Status
Workflow failed because of pom.xml file present inside a folder rather having in root directory of repository | Rectified
Workflow is unable to create a new directory for copying artifacts | Rectified
workflow has failed because of an outdated dependency (tws wrapper version 8.7) in pom.xml | Rectification in Progress